## Sheet1
Network on Chip methodology for designing and simulating neural network accelerator
THESIS START: | 2020-09-15
THESIS END: | 2021-03-15
TASK | START | END | September | October | November | December | January | February | March
TASK 1:Understanding the existing NN-Noxim with a focus on grouping neurons and mapping neurons to the processing elements | 2020-09-15 | 2020-10-21 | bar: September
TASK 2: Implementation of LeNet and VGG-16 architectures | 2020-10-22 | 2020-11-30 | bar: November
TASK 3:Table based routing for improving the performance considering faulty routers | 2020-12-01 | 2020-12-31 | bar: December
TASK 4:Evaluating the performance of the simulated model | 2021-01-01 | 2021-01-15
Report | 2021-01-16 | 2021-03-15 | bar: February to March